Risk Register

School:

Supervising teachers/staff:

Program/Excursion:	Go- Karts Program

Year Level:	10

Dates:	Term 2 and 4 during class time

Location(s):

Use the Risk Treatment Priority Table at the end of this document to determine the treatment priority.
Risk Description	Existing Controls	Rating			Treatment Priority[1]
Describe the risk event, cause/s and consequence/s. For example, / Something occurs … caused by … leading to …	Describe any existing policy, procedure, practice or device that acts to minimise a particular risk	Effectiveness of existing controls	Risk Consequences	Risk Likelihood	If control effectiveness is poor or unknown provide further treatment
Student hitting a tree or fence with Go-Kart caused by mechanical fault or human error leading to serious impact.	Have a designated track area not within 10 metres of trees or buildings. / Student training in place to minimise human error. Scrutineering is also carried out on vehicle before / Operation.	Satisfactory	Major	Rare	treat
Vehicle hitting uneven terrain or colliding with object caused by poorly prepared surface and human or mechanical error.	Surface preparation is carried out if track is in poor condition. Student training in place to minimise human error. Scrutineering is also carried out on vehicle before operation. Appropriate PPE (Personal Protective equipment) is to be worn. Students undertaking Driving licence before operation of vehicle and Go-kart isolation remote from safe area to be operated.	Satisfactory	Major	Rare	Treat
Accident without colliding with obstacle (e.g. frame breaking) caused by mechanical fault	Scrutineering is carried out on vehicle before operation.	Satisfactory	Moderate	Rare	Monitor
Chain becoming unattached and causing damage or injury or student acquiring injury from pinch hazard between chain and sprockets.	Go karts have to be fitted with appropriate chain guards and are scrutinised before operation. Students are educated about the risk of such injuries.	Satisfactory	Moderate	Rare	Monitor
Burn from exhaust or engine components of the go-kart, caused by contact with hot components of the go-kart.	Engine is not modified and has appropriate guarding and signage. Any modifications that have taken place are means of minimising the risk of the hazard.	Satisfactory	Minor	Rare	Monitor
Go-Kart coming into contact with people at speed caused by human error or mechanical fault leading to injury or causalities	Once Go-Kart is operational remaining students are to gather to a designated safe area while the Go-kart is in operation. Students are to remain in the safe area until instructed that is safe to leave the area. Students undertake a driver’s licence covering such aspects before operating the vehicle. Go-karts will be operated only during class time ensuring only student who hold a licence will be on the premises. Go-kart isolation remote from safe area is to be operated.	Satisfactory	Major	Rare	Treat
Moving Go-Kart colliding with another stationary Go-Kart caused by mechanical fault or human error leading to injury.	Stationary Go-Karts are parked in a designated safe parking area. Students have to obtain their drivers licence which covers these hazards the before operation of vehicle and Go-kart isolation remote from safe area is to be operated.	Satisfactory	Major	Rare	Treat
Moving Go-Kart colliding with another moving Go-Kart caused by mechanical fault or human error leading to injury.	Only one Go-kart is to be operational at a time. Students have to obtain their drivers licence which covers these hazards the before operation of vehicle.	Satisfactory	Major	Rare	Treat
Go-Kart becomes uncontrollable caused by mechanical fault (e.g. binding throttle or damaged steering components) resulting in collision and injury.	Kill switch has to be mounted to the vehicle to eliminate the hazard. The kill switch is scrutinised before operation of the vehicle as well as general scrutineering of the Go-Kart to ensure all components are operating correctly. Students also undertake training in preparation for when this issue may arise as well as the Go-kart isolation remote from safe area to be operated.	Satisfactory	Major	Rare	Treat
Go-Kart catching fire caused by fuel in contact with hot surface or flame. Leading to burns	Engine is not modified and in good condition. Dry powder fire extinguisher onsite.	Satisfactory	Moderate	Unlikely	Monitor
Foreign matter (track cone) coming into contact with driver causing injury when struck.	Driver is required to wear PPE including helmet that meets Australian standards AS1698 with a visor or a helmet and appropriate eye cover. Full cover footwear is also required to be worn.	Satisfactory	Minor	Unlikely	Monitor
Go-Kart being driven outside of designated track area becoming a hazard to other occupants and chance of hitting an obstacle outside the controlled area.	Students are made aware of the designated track area and consequences will be in place for those who choose to disobey the rules and the Go-kart isolation remote from safe area is to be operated.	Satisfactory	Moderate	Rare	Monitor
Students unaware of what is expected from them when driving on the track. Causing them to have no communication leading to an accident.	To obtain the licence students have to know the meaning of each different coloured flags when waved. This is to obtain communication between driver and marshals. / Green flag waved indicates the start of a driving session / Red flag waved indicates to the driver to stop where they are / Black flag is waved it indicates to the driver to pit in immediately.	Satisfactory	minor	Rare	Monitor

And more rows as required. This is one way of documenting the risk management process and does not preclude other approaches.
Risk Treatment Priority Table
Use the table below to decide the overall risk rating and represent the priority of the each risk for treatment.

Consequences	Major
	Moderate
	Minor
	Insignificant
		Rare	Unlikely	Likely	Almost certain
		Likelihood

Treat	Monitor